CASE MANAGEMENT SYSTEM

V1

Project Definition and Implementation Baseline

Case Workflow Management and Operational Monitoring

| Document Control | Definition |
| --- | --- |
| Document purpose | Define the project, the V1 delivery boundary, the technical approach, team ownership, implementation sequence, and acceptance basis. |
| System type | Internal web-based Case Workflow Management and Monitoring System. |
| Delivery baseline | V1 — the first controlled implementation baseline for the current delivery cycle. |
| Delivery model | Six development sessions with one Coordinator and four Developers. |
| Coordinator | Fahad |
| Core technology | ASP.NET Core MVC, ASP.NET Core Identity, Entity Framework Core, SQL Server, ClosedXML |

Prepared by: Fahad — Coordinator

1. Executive Summary

The Case Management System is an internal operational monitoring application designed to provide controlled visibility over cases that originate and are processed in an external source system. The application does not replace the source system and does not perform the underlying operational case work. Instead, it establishes a structured internal layer for case intake, user assignment, workflow tracking, operational follow-up, service-level monitoring, supervisory review, and audit history.

Cases enter the application through an Excel-based intake process. Each valid row is validated, matched to an Expert through the employee number maintained in ASP.NET Core Identity, and then stored as a Case assigned to that Expert. From that point onward, the system records the operational lifecycle of the Case: initial assignment, work updates, optional challenge handling, completion submission, Supervisor review, and final completion.

V1 is the first controlled implementation baseline. It is intentionally bounded to a complete end-to-end workflow that can be implemented, integrated, demonstrated, and evaluated within the current delivery cycle. The purpose of V1 is to establish the technical foundation and validate the core business process before additional capabilities are introduced in later iterations.

V1 outcome A successful V1 is a stable, reproducible application in which a Supervisor can create users and import cases, an Expert can work through the assigned case lifecycle, the system can monitor SLA status, and the full case journey can be reviewed through history and a basic operational dashboard.

2. Operational Context and Problem Definition

The operational work associated with a case takes place outside this application. This creates a management need that is separate from the source system itself: the organization requires a reliable mechanism to know which employee owns each case, what stage the case is currently in, what actions have been recorded, whether an operational challenge exists, whether the case is approaching or exceeding its SLA, and whether completion has been reviewed by a Supervisor.

Without a structured monitoring layer, these questions are difficult to answer consistently because assignment, progress, exceptions, completion, and performance indicators may be distributed across files, communications, or manual follow-up. The proposed system addresses that gap by turning imported external case data into a controlled internal workflow record.

2.1 Problem Statement

• Case data originates externally and must be introduced into the internal monitoring environment in a controlled form.

• The Case must be linked to the correct employee without relying on employee names, which may be duplicated or written inconsistently.

• Supervisors require a single view of ownership, workflow stage, progress, exceptions, completion status, and SLA performance.

• Experts require a focused view of their own assigned cases and a simple mechanism to record operational updates.

• Workflow changes must be traceable so the lifecycle of a Case can be reconstructed without inspecting raw database tables.

• Invalid or unmatched import rows must not create misleading assignments.

3. System Objectives and Solution Boundary

The system is designed as a monitoring and workflow-control layer around externally originated cases. Its responsibilities begin when case data is received for import and continue through internal follow-up until the Case reaches the V1 terminal stage of Completed.

| Objective | Definition |
| --- | --- |
| Controlled intake | Validate imported case data before it becomes an operational record. |
| Reliable assignment | Use EmployeeNumber to locate the correct ApplicationUser and persist the assignment using ApplicationUser.Id. |
| Workflow visibility | Maintain a clear stage for every Case and enforce the approved transitions. |
| Operational follow-up | Allow Experts to record updates while the actual case work remains in the external system. |
| Exception management | Provide a controlled Challenge path and an Import Needs Review path. |
| Completion governance | Require Supervisor review before an in-progress Case becomes Completed. |
| SLA monitoring | Calculate due dates, remaining time, delay status, and relevant stage durations. |
| Auditability | Preserve a meaningful history of assignment and workflow events. |
| Supervisory oversight | Provide read-only dashboard indicators and case visibility for operational monitoring. |

3.1 What the System Does Not Do

The application is not intended to become the operational processing system for the case itself. The Expert continues to perform the substantive case work in the external system. V1 records and governs the internal monitoring process around that work.

• It does not replace the external source system.

• It does not create cases manually as the normal intake method.

• It does not introduce a separate workflow stage called Delayed; delay is a calculated indicator.

• It does not implement self-registration.

• It does not include assignment Accept/Reject behavior.

• It does not include a Closed stage in V1.

4. Business Roles and Access Model

| Role | Purpose | Primary capabilities |
| --- | --- | --- |
| Supervisor | Administrative and supervisory role | Create/manage users; import cases; review all cases; resolve import review items; resolve challenges; review completion requests; access Dashboard. |
| Expert | Operational follow-up role | Access My Cases; view assigned Case details; add updates; start a Challenge; submit completion for Supervisor review. |

5. Case Intake and Assignment Model

The external Excel file is the V1 intake mechanism. It provides the minimum information required to create a Case record and identify the intended Expert. The intake process is intentionally separated into validation, preview, and persistence so that errors can be identified before they affect operational data.

| Required Excel field | Purpose |
| --- | --- |
| ExternalCaseId | External case identifier used to distinguish the source record and support duplicate prevention. |
| Title | Short case title. |
| Description | Concise description of the case. |
| SLAStartDate | External start timestamp used as the SLA timing baseline. |
| Priority | P1, P2, P3, or P4. |
| AssignedEmployeeNumber | Employee number used to locate the correct Expert. |

5.1 Assignment Rule

EmployeeNumber is used only to locate the correct ApplicationUser during import. The permanent relationship between the Case and the Expert is then stored using the ASP.NET Core Identity user identifier. This separates the external business identifier used for matching from the internal relational identifier used for persistence.

Assignment principle Excel EmployeeNumber → locate ApplicationUser → use ApplicationUser.Id as Case.AssignedExpertId.

5.2 Needs Review

If the imported EmployeeNumber does not match an eligible Expert, the system must not create a false assignment. The row is retained as an Import Review item so that a Supervisor can resolve the exception while preserving the original case data. General manual assignment is not part of V1; exception resolution exists only to correct an unresolved import.

6. V1 Operational Workflow

The V1 lifecycle is designed as a small, explicit state model. The normal path is linear, with two controlled exception loops: Challenge resolution and Supervisor return from completion review.

| Stage / activity | Primary actor | Operational meaning |
| --- | --- | --- |
| Validate & Preview | Supervisor | Validate file structure and row data before persistence. |
| Assigned | System | A valid imported Case is automatically assigned to the matched Expert. |
| InProgress | Expert | The first operational update starts active work tracking. |
| Challenge | Expert / Supervisor | An Expert records an operational blocker; the Supervisor resolves it and returns the Case to InProgress. |
| CompletionPending | Expert | The Expert submits a completion summary for review. |
| Supervisor Review | Supervisor | The Supervisor either returns the Case to InProgress with a reason or approves completion. |
| Completed | System / Supervisor action | The approved V1 terminal state. CompletedAt is recorded. |

6.1 Approved State Transitions

• Assigned → InProgress when the Expert records the first update.

• InProgress → Challenge when the assigned Expert records a valid challenge reason.

• Challenge → InProgress when the Supervisor resolves the challenge.

• InProgress → CompletionPending when the assigned Expert submits a completion summary.

• CompletionPending → InProgress when the Supervisor returns the Case with a reason.

• CompletionPending → Completed when the Supervisor approves completion.

• Completed is final in V1.

6.2 History and Traceability

The Case history is an operational audit trail rather than a decorative timeline. It must contain meaningful events for import and assignment, first update, challenge start and resolution, completion submission, return to work where applicable, and completion approval. The history must be understandable in chronological order without requiring the reviewer to interpret database internals.

7. V1 Delivery Scope

The V1 boundary identifies the capabilities that constitute the current implementation commitment. Features outside this boundary are not part of the present acceptance baseline.

| Capability | V1 status |
| --- | --- |
| ASP.NET Core Identity authentication | Included |
| Supervisor and Expert roles | Included |
| Supervisor-managed user creation and editing | Included |
| Excel .xlsx intake | Included |
| File, header, and row validation | Included |
| Preview before import | Included |
| Automatic Expert assignment by EmployeeNumber | Included |
| Needs Review for unmatched employee numbers | Included |
| All Cases / My Cases / Case Details | Included |
| Case updates and first-update transition | Included |
| Challenge start and Supervisor resolution | Included |
| Completion request, return, and approval | Included |
| Case history / timeline | Included |
| SLA status and delay calculation | Included |
| Supervisor-only read-only Dashboard with basic KPIs and filters | Included |
| Self-registration | Excluded from V1 |
| Accept / Reject assignment | Excluded from V1 |
| Closed workflow stage | Excluded from V1 |
| Advanced analytics / heat maps | Excluded from V1 |
| Scheduled or API-based import | Excluded from V1 |
| V1 design rationale The first release concentrates on the minimum complete operational workflow required to validate the solution architecture and the end-to-end business process. Extensions are deferred until the baseline workflow is stable and demonstrably reproducible. |  |

8. Technical Architecture

The solution uses a conventional ASP.NET Core MVC structure so that presentation, business rules, identity, and persistence remain clearly separated. Controllers coordinate requests, Services contain business logic, Models and ViewModels define persisted and screen-level data structures, and Entity Framework Core manages persistence to SQL Server.

| Architectural area | Responsibility |
| --- | --- |
| Presentation | Razor Views for Account, Users, Import, Cases, and Dashboard. |
| Request handling | MVC Controllers responsible for routing and authorization boundaries. |
| Business services | UserService, ExcelImportService, CaseService, WorkflowService, and SLAService. |
| Domain and UI contracts | ApplicationUser, Case, CaseUpdate, CaseChallenge, ImportReviewItem, workflow entities, SLA models, and ViewModels. |
| Data access | ApplicationDbContext, Entity Framework Core, Migrations, and Seeders. |
| Security | ASP.NET Core Identity authentication and role-based authorization. |
| Database | SQL Server for users, cases, updates, history, challenges, review items, workflow configuration, and SLA configuration. |

Figure 1. Case Management System V1 — Technical Architecture and Operational Flow

9. Project Structure and Principal Components

The project structure mirrors the architectural separation described above. The objective is not to create an unnecessarily complex architecture, but to keep each responsibility in a predictable location so that development ownership and integration can be controlled.

| Project area | Principal contents |
| --- | --- |
| Controllers | AccountController, UsersController, ImportController, CasesController, DashboardController |
| Services | IUserService/UserService, IExcelImportService/ExcelImportService, ICaseService/CaseService, IWorkflowService/WorkflowService, ISLAService/SLAService |
| Models | ApplicationUser, Case, CaseUpdate, CaseChallenge, ImportReviewItem, WorkflowStage, WorkflowTransition, CaseStatusHistory, SLAConfiguration |
| ViewModels / DTOs | Login and User Management contracts, Excel row/import contracts, Case list/detail contracts, Challenge/Completion contracts, SLA/Dashboard contracts |
| Data | ApplicationDbContext, Seed data, EF Core Migrations |
| Views | Account, Users, Import, Cases, Dashboard, Shared |
| Constants / Enums | Roles, workflow stage names, priorities, and other approved shared contracts |
| Documentation / Test evidence | README, security matrix, import test report, workflow test matrix, SLA/Dashboard test report |

9.1 Key Persisted Relationships

• ApplicationUser stores the employee identity, including EmployeeNumber and FullName.

• Case stores the external case identity, priority, SLA start, current workflow stage, and assigned Expert user identifier.

• CaseUpdate stores Expert follow-up entries associated with a Case.

• CaseStatusHistory stores meaningful lifecycle changes and supporting comments.

• CaseChallenge stores challenge timing, reason, and resolution data.

• ImportReviewItem preserves unresolved import data until the exception is resolved.

• SLAConfiguration stores the allowed duration for each priority baseline used in V1.

10. Delivery Team and Workstream Ownership

Delivery ownership is divided by functional workstream. Each Developer owns a coherent module across the six sessions, while the Coordinator owns cross-cutting integration, shared data-layer changes, migration sequencing, and end-to-end acceptance.

| Team member | Workstream | Primary ownership |
| --- | --- | --- |
| Fahad | Coordinator / Integration | Integration branch, shared configuration, database context, migrations, service registration, seed execution, branch integration, end-to-end verification, release readiness. |
| Daifallah | Developer 1 — Identity & Users | ApplicationUser and user contracts, authentication, role enforcement, user administration, Expert lookup support, identity validation, security verification. |
| Abdulmajeed | Developer 2 — Excel Import | Excel contracts, file/header/row validation, preview, persistence, automatic assignment, Needs Review, review resolution, import validation evidence. |
| Muath | Developer 3 — Case Workflow | Core Case/workflow entities, read-only case flow, updates, stage transitions, Challenge, completion workflow, history/timeline consistency. |
| Khalid | Developer 4 — SLA & Dashboard | SLA configuration and calculations, delay and duration logic, challenge-aware timing, Supervisor Dashboard, KPI/filter validation. |

10.1 Integration Dependencies

Some workstreams are intentionally dependent on shared components. These dependencies are sequenced rather than developed independently to avoid duplicate migrations, conflicting shared configuration, or runtime dependency-injection failures.

| Dependency | Reason |
| --- | --- |
| Developer 1 → Developer 2 | The real Excel import requires user lookup by EmployeeNumber. |
| Developer 3 → Coordinator | New workflow entities require DbContext integration and migration before they are consumed by persistence logic. |
| Developer 3 → Developer 4 | Challenge records and workflow history are required for challenge-aware SLA duration calculations. |
| All Developers → Coordinator | Session output is integrated one branch at a time and verified before the next merge. |
| Coordinator → All Developers | Shared migrations, service registrations, seeders, and the accepted integration baseline are redistributed through the shared development branch. |

11. Development and Integration Method

The project is implemented as a six-session incremental delivery. Each session produces a verifiable increment rather than a disconnected set of files. The sequence moves from foundation, to read-only capability, to the operational workflow, to exception handling, to completion and monitoring, and finally to release hardening.

| Control | Application |
| --- | --- |
| Branch synchronization | Each workstream begins from the latest accepted shared baseline. |
| Workstream ownership | Developers work primarily within their assigned module and avoid unnecessary shared-file changes. |
| Build verification | A successful build is required after material changes and before a session push. |
| Meaningful session push | Each team member produces a traceable GitHub push at the end of each session. |
| Controlled merge | The Coordinator merges one developer branch at a time and builds after each merge. |
| Shared database change control | Cross-module DbContext and migration changes are coordinated centrally. |
| Integration test | A feature is accepted only when it participates correctly in the end-to-end workflow, not merely when its individual files compile. |
| Release evidence | The final session produces repeatable tests and documentation for identity, import, workflow, SLA, and dashboard behavior. |

11.1 Git Workstreams

| Branch | Purpose |
| --- | --- |
| develop | Shared integration baseline used to synchronize workstreams. |
| coordinator-integration | Coordinator-controlled integration and cross-cutting changes. |
| dev1-identity-users | Identity and User Management workstream. |
| dev2-excel-import | Excel intake and import workstream. |
| dev3-case-workflow | Case lifecycle and workflow workstream. |
| dev4-sla-dashboard | SLA and Dashboard workstream. |

12. Six-Session Implementation Plan

| Session | Theme | Integrated outcome |
| --- | --- | --- |
| Session 1 | Foundation & Technical Contracts | Establish the running MVC solution, Git structure, shared packages/contracts, core models, Identity/SQL configuration, ApplicationDbContext, and initial migration. |
| Session 2 | Basic Features & Read-Only Flow | Make authentication usable, establish seed data and implemented service registrations, validate/preview Excel input, provide read-only case views, and establish basic SLA behavior. |
| Session 3 | Core Operational Flow | Complete the first end-to-end path: create Expert → import valid case → automatic assignment → Expert My Cases → first update → InProgress, with reusable SLA status. |
| Session 4 | Challenges, Needs Review & Authorization Hardening | Introduce unknown-employee review handling, the Challenge lifecycle, WorkflowService integration, authorization strengthening, and challenge-aware SLA timing. |
| Session 5 | Completion, Dashboard & Operational Polish | Implement completion request and Supervisor review, complete Needs Review resolution, add role-aware navigation, introduce the read-only Dashboard, and verify the complete business path. |
| Session 6 | Release Hardening, Testing & Handover | Introduce no major new feature; execute fresh-database validation, security/import/workflow/SLA test evidence, full UAT, README completion, final integration, and V1 release tagging. |

12.1 Session-by-Session Workstream Responsibilities

| Session | Fahad — Coordinator | Daifallah — Dev1 | Abdulmajeed — Dev2 | Muath — Dev3 | Khalid — Dev4 |
| --- | --- | --- | --- | --- | --- |
| S1 | Repository/branches; shared packages/contracts; integrate models; DbContext, Identity, SQL, initial migration. | ApplicationUser; login/create/edit user contracts; IUserService; Identity seed foundation. | Excel DTO/ViewModel; import service contract; file-level validation and upload foundation. | Core Case/workflow models; stage/history contracts; Case service contract. | SLAConfiguration; SLA status contract; SLA service foundation. |
| S2 | Integrate S1; register implemented services; run Identity/Workflow/SLA seeders; verify runtime and migration state. | Seed roles and initial Supervisor; Login, Logout, AccessDenied. | Exact header validation; row parsing/validation; Preview without creating Cases. | Read-only All Cases/My Cases/Details and case query service behavior. | Basic due-date, total-duration, remaining-time and service foundation. |
| S3 | Integrate first business path; register UserService; migrate CaseUpdate; execute cross-module scenario. | Implement UserService; Expert lookup by EmployeeNumber; create/list users. | Persist valid rows; automatic assignment; create initial history; operational import. | CaseUpdate; first update; Assigned→InProgress; updated Case Details/history. | Delay indicator; InProgress duration; reusable SLA status. |
| S4 | Integrate CaseChallenge and ImportReviewItem; register WorkflowService; migrate and test challenge/review paths. | Complete Edit User; verify Expert cannot access Supervisor User Management. | Create Needs Review path for unknown employees; harden import authorization/exception handling. | Challenge model and workflow; Expert starts, Supervisor resolves; same Expert retained; history recorded. | Calculate Challenge duration and include it in SLA status. |
| S5 | Integrate final workflow; migrate completion/review fields; role-aware navigation; full end-to-end scenario. | Display roles; polish user validation; role-based login destinations. | Import result summary; preserve original review data; Supervisor resolution of unresolved assignment. | Completion submission; return to work; Supervisor approval; Completed terminal behavior and history. | Supervisor-only Dashboard; KPI counts, filters, basic chart, case table. |
| S6 | Final merges; fresh DB test; full UAT; README; develop integration; V1 tag. | Security/Identity validation matrix and final authorization checks. | Final Excel test suite, database verification, friendly error handling, import test report. | Legal/illegal transition verification; final timeline consistency; workflow test matrix. | Numerical SLA verification; Dashboard count/filter validation; SLA/Dashboard test report. |

13. Practical Implementation Sequence

The following sequence describes how the V1 baseline is implemented operationally. It intentionally focuses on activities and verification points rather than code.

1. Confirm that the ASP.NET Core MVC solution builds and runs before feature development begins.

2. Establish the shared Git repository, development branch, integration branch, and four workstream branches.

3. Install and verify the common technology packages once at solution level.

4. Create the approved shared roles, workflow stages, priorities, and other technical contracts.

5. Develop the initial workstream models and interfaces in parallel.

6. Integrate persistent models into ApplicationDbContext and configure ASP.NET Core Identity and SQL Server.

7. Create and apply the initial database migration; verify that the required Identity and domain tables exist.

8. Seed the approved roles, workflow stages, SLA configuration, and the initial development Supervisor account.

9. Implement authentication and verify role-protected access behavior.

10. Implement Excel upload, file validation, header validation, row validation, and preview before persistence.

11. Implement read-only All Cases, My Cases, and Case Details views so that case ownership and stage can be inspected.

12. Implement UserService so the Supervisor can create Experts and the import process can resolve EmployeeNumber.

13. Enable real Excel persistence, automatic assignment, initial Assigned stage, and initial history creation.

14. Enable Expert updates and move the Case from Assigned to InProgress on the first valid update.

15. Introduce Needs Review for rows that cannot be matched to an eligible Expert.

16. Introduce Challenge start and Supervisor resolution while preserving the assigned Expert.

17. Introduce completion submission, Supervisor return-to-work behavior, and Supervisor approval to Completed.

18. Complete SLA timing, Challenge duration, delay status, and the Supervisor Dashboard.

19. Run the full integrated business scenario using a clean test Case and verify the resulting Case history.

20. Rebuild a fresh database from the migration chain, rerun seeders, execute final UAT and module test evidence, and tag the accepted V1 release.

14. Acceptance and Evaluation Baseline

The V1 implementation should be evaluated against observable system behavior rather than the presence of individual source files. The following acceptance conditions represent the minimum evidence that the planned baseline has been achieved.

| Acceptance area | Evidence of completion |
| --- | --- |
| Foundation | Project builds with zero errors; required services are registered; a fresh database can be created from the migration chain. |
| Identity | Supervisor and Expert login work; no self-registration exists; Supervisor can manage users; protected Supervisor routes reject Expert access. |
| Excel intake | Required headers and row values are validated; preview works; invalid workbooks fail safely. |
| Assignment | A valid EmployeeNumber resolves to the correct Expert; the persisted Case relationship uses ApplicationUser.Id. |
| Needs Review | Unknown EmployeeNumber does not create a false assignment; the review item preserves original case data for resolution. |
| Case access | Supervisor can view all cases; Expert can view assigned cases; case details show stage, ownership, history, and relevant actions. |
| Operational updates | The assigned Expert can add an update; the first update changes Assigned to InProgress and creates history. |
| Challenge | The assigned Expert can start a Challenge with a reason; the Supervisor can resolve it; the Case returns to InProgress with the same Expert. |
| Completion | The Expert can submit completion from InProgress; the Supervisor can return it with a reason or approve it to Completed. |
| History | The Case timeline contains a complete and chronologically understandable sequence of major lifecycle events. |
| SLA | Due date, remaining time, delay status, InProgress duration, and Challenge duration are consistent with the configured rules and recorded timestamps. |
| Dashboard | Supervisor-only KPI counts and filters match the underlying Case data; the Dashboard remains read-only. |
| Release evidence | Security, import, workflow, SLA/Dashboard tests are documented; full UAT passes or any defect has an owner and is resolved before release. |

14.1 Final End-to-End UAT Scenario

1. Supervisor logs in.

2. Supervisor creates an Expert.

3. Supervisor imports a valid Excel Case for that Expert.

4. The Case is automatically assigned and appears as Assigned.

5. Expert logs in and sees the Case in My Cases.

6. Expert records the first update; the Case becomes InProgress.

7. Expert starts a Challenge; Supervisor resolves it; the Case returns to InProgress.

8. Expert submits completion; Supervisor returns the Case with a reason.

9. Expert adds another update and submits completion again.

10. Supervisor approves completion; the Case becomes Completed and CompletedAt is populated.

11. The Case history explains the complete lifecycle.

12. SLA values and Dashboard counts reflect the final Case state.

15. Delivery Assumptions, Constraints, and Controls

| Area | Delivery consideration | Control |
| --- | --- | --- |
| External source dependency | The source system remains authoritative for the original case record and V1 receives data through Excel. | Preserve ExternalCaseId and SLAStartDate from the source row. |
| Employee matching | Names are not reliable enough for assignment. | Use EmployeeNumber for lookup and ApplicationUser.Id for persistence. |
| Shared database changes | Parallel migrations can conflict. | Coordinator controls cross-module DbContext integration and migration sequencing. |
| Cross-workstream dependencies | Some features cannot compile or run until a shared service/entity exists. | Integrate dependency-producing work early and redistribute through the shared baseline. |
| Scope expansion | Adding advanced features during the six sessions can destabilize the baseline. | Treat the V1 boundary as the controlled acceptance scope. |
| Authorization | Hidden links alone do not protect functionality. | Enforce controller/action authorization and test direct URLs. |
| Import quality | External files may contain invalid, duplicate, or unmatched rows. | Validate before persistence, block duplicates, and use Needs Review for unresolved assignments. |
| Release reproducibility | A development database can hide migration or seed defects. | Rebuild a fresh database during Session 6 and rerun the full migration chain and seeders. |

15.1 Release Quality Rules

• No unresolved Git conflict markers.

• No major feature introduced during Session 6.

• No runtime dependency-injection failure.

• No invalid workflow transition that corrupts the current Case stage.

• No incorrect assignment for an unknown EmployeeNumber.

• No production credential documented in project handover material.

• All final acceptance evidence is reproducible by another team member using the repository and README.

16. Post-V1 Evolution

V1 establishes a stable operational baseline rather than the final ceiling of the system. Once the workflow and data model have been validated in practice, the same architecture can support additional capabilities without redefining the core Case ownership and history model.

Capabilities intentionally excluded from V1 provide a natural roadmap for later releases. These may include scheduled or API-based source integration, richer analytics and heat maps, additional reporting, notifications, and a later Closed stage if the operational process requires a distinction between completion approval and administrative closure.

Baseline principle Future releases should extend the accepted V1 lifecycle rather than bypassing its identity, assignment, workflow-history, authorization, and data-integrity rules.

17. V1 Deliverables

• ASP.NET Core MVC source code organized by the approved workstreams.

• SQL Server database schema reproducible through Entity Framework Core migrations.

• Identity, workflow, and SLA seed data required to initialize the application.

• Excel import format and validation behavior for the V1 intake contract.

• Operational workflow from Assigned through Completed, including Challenge and return-to-work paths.

• Role-based Supervisor and Expert user journeys.

• Case history sufficient to reconstruct the lifecycle of a test Case.

• Supervisor-only SLA monitoring Dashboard.

• README with reproducible setup instructions.

• Final Identity/Security, Import, Workflow, and SLA/Dashboard test evidence.

• Full UAT record and accepted V1 release tag.

Project baseline statement This document defines the Case Management System V1 delivery baseline against which implementation progress and final achievement can be assessed. The accepted V1 is the complete, integrated behavior described in this document—not the broader set of capabilities that may be introduced in future releases.